PROJECT_1  MVP DEFINITION & PRODUCT ROADMAP

AI-Powered Predictive Quality Control

What we build first, why we build it, and what comes next.

01  MVP Goal & Success Criteria

| 1 Production Line Pilot scope | 3 Months Time to deploy | €150,000 Implementation budget | €500K+ Savings needed for board approval |
| --- | --- | --- | --- |

MISSION STATEMENT

Prove 20% defect reduction on ONE production line in 3 months, creating undeniable evidence that justifies a €150,000 budget for plant-wide rollout across all 12 lines.

Success Criteria

| Type | Criteria |
| --- | --- |
| Quantitative | Defect rate: 4.1% → <3.3% (20% improvement, validated by data over 3 months) |
|  | False positive rate: <10%, Michael's hard requirement (above this, operators ignore alerts) |
|  | System uptime: >99% (zero tolerance for production downtime caused by our system) |
|  | Alert latency: <100ms (real-time, not batch, a delayed alert is no alert) |
| Qualitative | Klaus uses dashboard daily without being prompted after week 2 |
|  | Klaus follows AI alert recommendations ≥80% of the time (adoption = trust) |
|  | Michael references quality score in weekly production meetings to his C-suite |
| Business | €500,000+ demonstrated savings in pilot period → board approves plant-wide budget |

02  MVP Features (11 Features | 3-Month Build)

Why these 11? Every feature in the MVP was selected because it scores ≥15 on RICE, directly solves Klaus, Sarah, or Michael's #1 pain point, and can be built in ≤1 month of engineering effort. Nothing else made the cut.

| ID | Feature | RICE | Why It's in MVP |
| --- | --- | --- | --- |
| F02 | SMS / Email Alerts | 54.0 | Highest RICE. Klaus needs instant notification, he can't watch a screen 24/7. 2-week build. |
| F04 | Cost Savings Calculator | 50.0 | Only product on market showing live EUR savings. Michael needs this to get board approval. |
| F01 | Real-time Defect Score | 22.5 | Core product value. Every other feature depends on this. Must be in v1. |
| F05 | Quality Dashboard | 19.0 | Visual centrepiece. Klaus shows to visitors. Michael checks from his office. |
| F31 | FPY Tracking | 18.0 | Michael's #1 board metric. Takes 1 month to build. High RICE for low effort. |
| F07 | 7-Day Trends | 18.9 | Pattern identification (Sarah). Shift management (Michael). 3-week build. |
| F06 | Tool Wear Prediction | 21.0 | Prevents 23% of failures. Uses data already collected. High ROI, low effort. |
| F03 | Root Cause Analysis | 17.1 | Explainability = trust = adoption. Without this, Klaus ignores alerts. Differentiates from SAP. |
| F27 | Quality Audit Trail | 34.2 | IATF 16949 legal compliance requirement. Must-have in Germany. 2-week build. |
| F16 | German / English UI | 54.0 | Germany-first requirement. Zero friction for Klaus's team. 2-week build. |
| F18 | Excel Export | 28.0 | Bridge to SAP. One-click, 2-week build. Klaus needs this. |

03  Features NOT in MVP (And Exactly Why)

This is where PM judgment shows. Any PM can say what to build. Top PMs explain what NOT to build and why. Every 'no' in MVP creates a faster, higher-quality 'yes' for something more important.

| ID | Feature | Why NOT in MVP | When |
| --- | --- | --- | --- |
| F10 | Visual AI (Cameras) | Requires €30K camera hardware + 2-month procurement + installation. Sensor-based model covers 80% of defect types. Zero CapEx advantage lost. | v2.0 Month 4-6 |
| F09 | SAP Integration | SAP APIs alone take 2-3 months of engineering. Excel export bridges the gap. Klaus admits he doesn't trust SAP data anyway. | v1.5 Month 4 |
| F11 | Mobile App | Responsive web dashboard works on mobile browser. Native app is polished, not value. Build when users specifically demand it. | v2.0 if demanded |
| F15 | Predictive Maintenance | Different problem, different stakeholders, different budget. Scope creep kills pilots. Not our product to build in v1. | v3.0 partnership |
| F20 | AR Overlay | RICE score: 0.63 (lowest of 50 features). Average inspector age: 58. High effort, very low adoption probability. | Backlog / Dropped |
| F44 | MES Integration | Complex system integration. Different data format per factory. Needed for enterprise scale but premature for single-line pilot. | v2.0 Month 7 |

05  Product Roadmap (12 Months)

Strategy: Prove → Scale → Advanced → Enterprise. Each phase only starts when the previous phase achieves its success metrics. No phase skipping.

| Q1 2026 MVP, Single Line Goal: Prove concept on Line 3 Target: €500K savings | - Real-time defect scoring = core ML model, 10-second intervals - SMS + Email alerts = instant notification below threshold - Root cause analysis = top 3 factors, plain language - Cost savings calculator = live EUR impact dashboard - Quality dashboard = web-based, responsive - 7-day trends + FPY tracking = historical patterns - Tool wear prediction = alert at 180 min not 240 - Compliance + export = IATF audit trail, Excel export |
| --- | --- |
| Q2 2026 v1.5, Scale to 3 Lines Goal: Scale validated system Target: €2M savings | - SAP QM data export (automated) = scheduled sync, no manual step - Shift performance comparison = morning / afternoon / night view - Production line comparison = Lines 1, 3, 7 side-by-side - OEE integration = quality score + equipment effectiveness - False alarm feedback loop = operators train model via feedback - Automated management reports = weekly PDF to Michael - IATF 16949 / VDA compliance reports = auto-generated for audits |
| Q3 2026 v2.0, Advanced Features Goal: Deepen value per plant Target: €5M savings | - Visual anomaly detection (cameras) = CNN model on camera feed - Full SAP QM integration = bi-directional API sync - Mobile app (iOS + Android) = native push notifications - Predictive maintenance link = quality + machine health combined - MES integration = bi-directional manufacturing system sync - Multi-plant dashboard = all sites in single view |
| Q4 2026 v3.0, Enterprise Platform Goal: Platform + partnerships Target: €10M ARR | - Customer portal (BMW / Daimler) = OEM-facing quality visibility - Supplier quality tracking = defects traced to material batches - Cross-plant benchmarking = best plant performance as target - API platform = 3rd party integrations and custom workflows - What-if scenario simulator = 'change torque by 10%' impact prediction - AI model marketplace = industry-specific pre-trained models |

Phase Gate: Each phase only begins when the previous phase hits its financial target. This prevents scope creep and ensures every build decision is grounded in proven ROI, not roadmap optimism.

06  3-Month Build Timeline (MVP Only)

| Week | Month 1 — Foundation | Month 2 — Core Features | Month 3 — Deploy & Validate |
| --- | --- | --- | --- |
| Wk 1-2 | Sensor data pipeline + data ingestion | Quality dashboard UI build | Beta release to Klaus's team |
| Wk 3-4 | ML model training + validation (87%+ accuracy) | Alert system (SMS/Email) + Root cause | User training + feedback collection |
| Wk 5-6 | Model deployment to edge (factory floor) | Cost calculator + FPY tracking | Bug fixes + performance tuning |
| Wk 7-8 | Data quality checks + feature engineering | Excel export + audit trail + German UI | 3-month results analysis + board presentation |
| Wk 9-10 | — | Tool wear prediction alerts | Pilot success validation vs success criteria |
| Wk 11-12 | — | Testing + QA | v1.5 scope definition + budget request |